## Slide 1: National Association of Clean Water Agencies 2005 Developments in Clean Water Law Santa Fe, New Mexico November 9-11, 2005
Construction Law:
Managing Risks and Dealing With Disputes
Neal J. Sweeney

## Slide 2: Construction Law: Managing Risks and Dealing With Disputes
Who pays for defective design?
Special risks of underground construction/ tunneling
Dispute Review Boards
Risks of multi-prime contracting
Termination for default

## Slide 3: Who Pays for Defective Design?

## Slide 4: Who Pays for Defective Design? Build to Design
The Liability Gap
OWNER
GEOTECH
DESIGNER
SUBCONSULTANTS
SUBCONTRACTORS
CONTRACTOR
Warranty –Strict Liability–
Professional
Negligence
Professional Negligence

## Slide 5: Owner’s Liability to the Contractor
Spearin Doctrine:Implied warranty of the Adequacy of the plans & specifications
Liability is not based on owner’s authorship
In theory: Strict liability
Damages + causation = Owner liability
Limitations on liability
  Patent defects (knew or should have know)
  Contract risk shift to contractor:
    Duty to find, not just advise of known defects
    Reliance on contractor's expertise
  Duty to mitigate

## Slide 6: Contractor's Potential Liability for Design
  Performance Specifications
    Design/Build Responsibility
    Design Specifications vs. Performance Specifications
  Shop Drawings
    Liability for Design Changes
    Designer Approval is not  Acceptance of Liability
    What Constitutes a Design Change?
  Secondary Design Review
    “Fill in the Gaps”
    Field Coordination
    Patent Defects
    Permits, Codes & Regulations

## Slide 7: Who Pays for Defective Design? Build to Design
The Liability Gap
OWNER
GEOTECH
DESIGNER
SUBCONSULTANTS
SUBCONTRACTORS
CONTRACTOR
Warranty –Strict Liability–
Professional
Negligence
Professional Negligence

## Slide 8: Designer’s Liability to Owner
Breach of contract, but judged on a professional negligence standard
Professionals are not supposed to be perfect
Owner must demonstrate
  The applicable standard of care
  That the designer violated the standard of care
  That the negligence was the proximate cause of the Owner’s damages
The Owner’s “Liability Gap”: Liability to the Contractor but no recovery against Designer

## Slide 9: Standard of Care
Design Functions
Baseline For Evaluating Negligence
Only Applicable If No Guarantees/Warranties
Even If Unstated, It Applies
Standard of Care May Be Raised
  By Express Statement
  By Special Expertise
Construed As Performance Guarantee?
Notes: 12

## Slide 10: Standard of Care
Specific?
  The “Care And Skill Ordinarily Used By Members Of The Engineering Profession Practicing Under Similar Conditions And At The Same Time And Locality.”
Notes: 13

## Slide 11: Performance Guarantees
An obligation that all or part of the project will perform in a certain way
Strict liability
Product output, energy usage, pollution discharges
Construction costs?
Enforceable if clear & unambiguous
Generally not insured under a standard E&O policy
Notes: 10

## Slide 12: Who Pays for Defective Design? Build to Design
The Liability Gap
OWNER
GEOTECH
DESIGNER
SUBCONSULTANTS
SUBCONTRACTORS
CONTRACTOR
Warranty –Strict Liability–
Professional
Negligence
Limitations of Liability
Thin Capitalization
E&O Coverage

## Slide 13: Other Issues Affecting Designer Liability
Contract Limitations on Liability
E&O coverage
Flow-down liability to consultants
Practical considerations:
  Thin capitalization &/or limited E&O coverage
  Owner’s deeper pockets

## Slide 14: Who Pays for Defective Design? Build to Design
The Liability Gap
OWNER
GEOTECH
DESIGNER
SUBCONSULTANTS
SUBCONTRACTORS
CONTRACTOR
Warranty –Strict Liability–
Professional
Negligence
Economic Loss Rule
Third Party Beneficiary

## Slide 15: The Designer’s Direct Liability to the Contractor
Contract theory; third part beneficiary
  Generally barred by the design contract
  Still judged under professional negligence
Tort theory: Negligence
  Professional negligence standard
  Economic Loss Rule, where applicable, may bar negligence claims for economic damages (no property damage or personal injury) – Always evolving
Fraud/ Misrepresentation – Intentional torts, not Negligence, and not E&O

## Slide 16: Bridging the Liability Gap for Design Design-Build?
Performance guarantees are the best way to shift design liability
Most standard design-build still maintain professional negligence as the standard for design liability
Other considerations affecting design liability
  Limitations Imposed on Design
  Superior Knowledge
  Partial Design
  Terms of Solicitation
  Information Provided
  Terms of the Contract

## Slide 17: Risk Management In Tunnel Construction

## Slide 18: Underground Construction A Risky Business
Subsurface conditions cannot be predicted precisely prior to bidding and construction
The geology largely dictates means & methods, costs and duration
Unlike above-ground construction, tunnels never “get out of the ground”
Linear – everything is critical; no work around
As much as 2/3 to 3/4 construction cost in “means and methods”
Owners typically stay out of contractor’s “means and methods”

## Slide 19: Procedures For Minimizing And Resolving Claims And Disputes
Differing site conditions (DSC) provision
Geotechnical Baseline
Escrow Bid Documents
Disputes Review Board (DRB)

## Slide 20: Differing Site Conditions Provision
Indicated conditions
Actual conditions encountered
“Material” difference
Impact to contractor’s operations
Causation
Damages

## Slide 21: Recommendations For Providing Subsurface Information
Make all relevant information available
Avoid disclaimers
Geotechnical Data Report (“GDR”)
Geotechnical Interpretive Report (“GIR”)
Geotechnical Design Summary Report (“GDSR”)
Geotechnical Baseline Report (“GBR”)

## Slide 22: Geotechnical Data Report
“Just the facts, Ma’am”
What was done
How it was done
What was learned

## Slide 23: Geotechnical Baseline Report
Provides data and interpretation
  Sets out designer’s anticipated subsurface conditions and impact on design and construction
  Presents advantages and disadvantages of various construction methods
Contains “baseline” statements – single, contractually-established interpretation of conditions
  Risk < baseline on contractor
  Risk > baseline on owner

## Slide 24: Geotechnical Baselines Are They Working?
Touted benefits
  Contractually (and clearly) establishes the “anticipated” conditions for DSC purposes
  Insures a level playing field for bidders
  Allows owner flexibility with risk assumption and financial goals
  Allows owner greater influence on means and methods
Issues
  Reliance
  Materiality
  Contractual mechanisms for effective use

## Slide 25: ESCROW BID DOCUMENTS
Purpose: Addresses reliance & damages
Ownership
Lessons learned
  Clearly identify key bid assumptions
  Highlight any variance from baseline
  “Fill-in-the-blank” for key variables in change orders and claims (advance rate, penetration rate, utilization, cutter usage, etc.)

## Slide 26: Disputes Review Board
“Real time” dispute resolution
Principals Have Less Control: Dispute Is “Judged”
Technical expertise vs. disputes resolution skills
Concerns regarding neutrality, claimant’s forum and “splitting the baby”
Selection process: Get it established early
Keeping the DRB involved and informed on the project
Level of formality and procedure
Scope of DRB’s authority: technical vs. legal issues
Notes: SCOPE: all disputes vs. only technical issues (like Metrowest)
If you do limit scope to technical issues, must have another ADR procedure for other issues
Fees: total cost is generally less than ½ of 1% of construction cost
Lesson Learned: take great care in selection – DRB only as good as its individual members
understand it is not a court – it is a settlement process

## Slide 27: Disputes Review Board
Impact of DRB decision?
  Non-Binding?
  Admissible in Court?
  Controlling pending outcome of litigation – cash flow?
  Binding arbitration?
Use In Conjunction With Mediation
Notes: SCOPE: all disputes vs. only technical issues (like Metrowest)
If you do limit scope to technical issues, must have another ADR procedure for other issues
Fees: total cost is generally less than ½ of 1% of construction cost
Lesson Learned: take great care in selection – DRB only as good as its individual members
understand it is not a court – it is a settlement process

## Slide 28: Multi-Prime Contracting The Problem
Two Scenarios:
  True Multi-prime:contract Direct With Trade Contractors, Typically Subs
  Multiple GC’s on Single Site And/or With Interdependent Scopes of Work
Most of the Legal Principles and Practical Considerations Are the Same
Notes: 22

## Slide 29: Multi-Prime Contracting The Problem
Creates a Coordination Vacuum Where The GC Once Stood
Owner Now Assumes Implied Duty to Coordinate
Most Owners Are Not Staffed to Provide Required Level of Project Management
Owner Can Engage Outside Expertise
Still an Increased Risk of Performance Problems and Claims
Notes: 22

## Slide 30: Multi-Prime Contracting The Owners’ Response
Disclaim The Implied Duty To Coordinate
Require Contractors To Coordinate - One And/or All
Make the Contractors Third Party Beneficiaries of Each Others Contracts & Bonds
Require Contractors To Sue Each Other
Hold Harmless and Indemnify the Owner
Notes: 23

## Slide 31: Multi-Prime Contracting New Problems
Trade Contractors Lack Power to Enforce Coordination: Inspect/Reject...Purse Strings...T4D
Agency CM (Owner’s Agent) Not The Same as GC
Increased Prospect of Litigation & Disputes
Owner Disclaimers Frequently Enforced
Regardless of Legal Result, What is The Impact On The Project?
Notes: 23

## Slide 32: TERMINATION FOR DEFAULT The Capital Punishment of Construction
Notes: 25

## Slide 33: Termination For Default
A Last Resort
Not Favored By The Law
Terminate & Your Actions Will Be Strictly Reviewed & Second- Guessed
The Acting Party Has The Burden Of Proof
Potential Exposure Is Can Be Substantial
There Will Be A Lawsuit & Counterclaim
Notes: 26

## Slide 34: The Termination Clause “The Prenuptial Agreement”
Flexibility
Termination For Convenience
Constructive Termination
Bases For Termination - Not Limited
Procedures: Notice, Cure Period, Meetings, Certification
Subcontracts: Assignments & Incorporation
Rights & Obligations Upon Termination
Notes: 28

## Slide 35: Termination For Default
Legal Issue: Can You Terminate?
Practical Issue: Should You Terminate?
Notes: 29

## Slide 36: Termination For Default Grounds For Default
Failure Or Refusal To Prosecute The Work
Failure To Complete On Time
Failure To Pay Subs & Suppliers
Abandonment
Failure To Cure Default
IT MUST BE A MATERIAL BREACH!!!
Notes: 30

## Slide 37: Termination For Default Defenses
Excusable Delay
Impossibility/ Defective Specifications
Cardinal Change
Lack Of Payment
Waiver
Procedural defects
Notes: 31

## Slide 38: Should You Terminate?
Cost Of Replacement
Time Impact On Project
Impact To Other Contractors
Long Lead Items
Favorable PO’s & Subcontracts
Warranty & Long Term Liability Issues
Notes: 32

## Slide 39: Termination for Default Dealing with The Surety
Law Of Suretyship, Not Insurance
Termination Should Not be The First Notice
Surety’s Options
  Complete
  Pay To Complete Up To Penal Sum
  Refuse To Complete
Litigation/ Arbitration/ Bankruptcy
Notes: 33

## Slide 40: Properly Implementing The Termination For Default
Plan To Complete, Not Plan To Terminate
Exhaust All Other Options
Consider: Facts, Contract, Bond, Applicable Law, & Best interests Of The Project
Answer: Can I / Should I terminate?
Give Ample Opportunity To Cure
Strictly Adhere To Procedures …Plus
Notes: 34

## Slide 41: Reprocurement
Be reasonable: Not A Blank Check!
Clearly Define Scope Of Work
Additional Scope: Separate Accounting
Survey Of Work In Place
Document Defective Work
Warranties
Assignment Of PO's & Subcontracts
New Bonds
Notes: 35

## Slide 42: Thank You!
Notes: 36

## Slide 46: National Association of Clean Water Agencies 2005 Developments in Clean Water Law Santa Fe, New Mexico November 9-11, 2005
Construction Law:
Managing Risks and Dealing With Disputes
Neal J. Sweeney, Esq.
Kilpatrick Stockton LLP
Suite 2800 1100 Peachtree St.
Atlanta, GA 30309-4530
(404) 815-6616
nsweeney@kilpatrickstockton.com
www.KilpatrickStockton.com