## Slide 1: The Ten Most Important Provisions Of Every Construction Contract
John I. Spangler III, Esq.
Alston & Bird, LLP

## Slide 2: The Business Terms
Scope of the Work
  Refer to the Contract Documents
  Do not include Proposal
  Be Careful of Exclusions and Qualifications
Completion Dates
  Use Specific, Enforceable Dates
  Define the Dates with Precision
  Address Liquidated Damages
Notes: SUB - Track scope through, general requirements, bids, quotes
  not fill in the blank process
  correct design development (fast track)
  Specs have contract provisions
  (Allowance) bids Kor proposals incorp (outdated, ________)
  Exhibits re: work, letters, etc. (time disconnect)
  GMP contracts special (Q&E exhibit)
SUB - expressly list dates for LD’s & amount
  failure of definition
  what does it meant to “Complete”
  dates as aspirations, conditions precedent like drug completion
  milestones - damages?? Cumulative LD’s??

## Slide 3: Delays and Delay Damages
Time Extensions - Critical Path Analysis
Delay Damages
  - Define the Damages
  - No Damages for Delay
  - Careful of Disruption Claims
  - Be Aware of Exceptions to No Damage for Delays
  - Limit to Extended GC’s
Force Majeure Issues
Notes: SUB - Notice of extension - Owner has to grant extension first
Time Extensions
  what delays trigger, affect critical path only (float)
  Abnormal weather only
SUB - same restrictions on damages, owner must pay damages
Damages
  no damages for delay (enforceable but exceptions)
  limit damages (no home office overhead/Eichleag claims)
  liquidated damages (considers full range of damages)
  AIA forms EXCLUDE consequential damages

## Slide 4: Limited Delay Damages Clause
In the event of delay, interference, disruption or inefficiency in the work caused by the Owner, the Engineer or any of their consultants or employees, or in the event the Contractor claims that its operations were accelerated, resequenced, impacted, or made less efficient or more expensive, the Contractor shall be entitled to an equitable extension of the Contract Time to cover delays in the critical path activities of the Work, and shall be entitled to recover compensation or damages only for actual increases in cost for project site personnel, project site equipment, project site labor and other miscellaneous general condition expenses at the project site directly caused by the delay. In no event shall Contractor be entitled to home office overhead, lost profits, loss of use of capital or any other type of consequential damages.

## Slide 5: Indemnity
Indemnity Related to Performance
Indemnity Related to Insurable Claims (Injuries to Persons/Property)
Notes: SUB
  Proper insurance coverage
  Same brand indemnity
  Dangerous work
  Insurable provision (injuries to persons/property)
  Breach of contract damages
  No sole negligence (13-8-2) (No rewrite)
  Attorney’s fees
  Surety bond coverage & perhaps insurance

## Slide 6: Indemnity
Indemnity Related to Performance
- increases scope of damages
- attorney fees may be recoverable
Notes: SUB
  Proper insurance coverage
  Same brand indemnity
  Dangerous work
  Insurable provision (injuries to persons/property)
  Breach of contract damages
  No sole negligence (13-8-2) (No rewrite)
  Attorney’s fees
  Surety bond coverage & perhaps insurance

## Slide 7: Standard Indemnity Language (Related to Performance)
The Contractor hereby agrees to defend, indemnify and hold the Owner harmless from any and all claims, suits, liens, demands, debts, damages, loss or expense, including, but not limited to, attorney’s fees and litigation expenses, suffered or incurred by the Owner as a result of the Contractor’s failure to perform in accordance with the Contract Documents.

## Slide 8: Indemnity
  B. Indemnity Related to Insurable Claims (Injuries to Persons/Property)
Notes: SUB
  Proper insurance coverage
  Same brand indemnity
  Dangerous work
  Insurable provision (injuries to persons/property)
  Breach of contract damages
  No sole negligence (13-8-2) (No rewrite)
  Attorney’s fees
  Surety bond coverage & perhaps insurance

## Slide 9: Standard Indemnity Language (Related to Insurable Claims)
The Contractor shall indemnify, hold harmless, and defend the Owner, the Owner's project manager (if any), Engineer and all of their agents, employees, consultants, parent subsidiaries or affiliated companies, successors and assigns from and against claims, damages, losses and expenses (including, but not limited to, attorneys' fees) arising out of or resulting from performance of the Work, but only to the extent such claims involve injuries to persons and/or property and are caused in whole or in part by negligent acts or omissions of the Contractor, a Subcontractor, a Sub-Subcontractor, a material or equipment supplier, or anyone directly or indirectly employed by them or anyone for whose acts they may be liable, regardless of whether such claim, damage, loss or expense is caused in part by a party indemnified hereunder.

## Slide 10: Notice Provisions
Contractor Should Provide Written Notice of Any Claim for Extra Time or Extra Compensation
Claim Is Waived If Notice Not Provided
Notes: SUB - Timing, given Kor enough time to pass it on
Notice within 10 days of claim for more money,
or more time, OR WAIVED
Tell me about issues while cheap - no and of project claims
Make sure consistent throughout (AIA doesn’t)
Waiver is a big problem - do paperwork later

## Slide 11: Notice Provision
If the Contractor believes it is entitled to an increase in the Contract Sum, or an extension of the Contract Time, or believes it has any other claim for monetary compensation, damages or time extensions from the Owner, the Contractor shall give the Owner written notice of such claim within ten (10) days after the occurrence giving rise to such claim. The notice required by this Paragraph is a condition precedent to the assertion of any claim by the Contractor. If the Contractor fails to give the Owner timely written notice of a claim, as required by this paragraph, the contractor will be deemed to have waived the claim, and the Owner shall have no further liability respecting the claim.

## Slide 12: Termination
Termination for Convenience
Termination for Cause
Notes: SUB
  Proper insurance coverage
  Same brand indemnity
  Dangerous work
  Insurable provision (injuries to persons/property)
  Breach of contract damages
  No sole negligence (13-8-2) (No rewrite)
  Attorney’s fees
  Surety bond coverage & perhaps insurance

## Slide 13: Termination Clause
(A) The Owner may terminate the Contract for convenience at any time upon written notice to the Contractor. In the event of a termination for convenience, the Contractor shall take immediate steps to terminate the Work as quickly and effectively as possible and shall terminate all contracts and objections to third parties unless otherwise instructed by the Owner. Provided that no damages are due to the Owner for Contractor’s failure to perform in accordance with the Contract, the Owner shall pay the Contractor for all Work performed to the date of termination, including reasonable overhead and profit for that portion of the Work, and for any other expenses incurred by the Contractor in terminating its activity at the Project site, and the Owner shall have no further liability to the Contractor for such termination.

## Slide 14: Termination Clause
(B) The Owner may terminate the contract for cause if the Contractor breaches any material provision of the Contract Documents. The Owner shall give the Contractor seven (7) days written notice of its intent to terminate the Contract, and, if the Contractor fails to cure the default within that period, the termination shall take place without further notice. In the event of a termination for cause, the Contractor shall not be entitled to further payment until the Work is completed by others. If the cost of completing the Work, combined with previous payments to the Contractor, is less than the Contract Price, the Contractor shall be paid the difference. If the cost of completing the Work, combined with previous payments to the Contractor, exceeds the Contract Price, the Contractor shall pay the difference to the Owner.

## Slide 15: Termination Clause
(C) If the Owner terminates the Contract for cause, and it is later determined that the Owner did not have grounds to do so, the termination will be treated as a termination for convenience under the terms of this Paragraph.

## Slide 16: Progress Payments
Effective Claim Waivers
Updated Schedules
Updated Submittal Logs/Procurement Schedules
Progress Report
Payment Period
Notes: SUB - get the same info owner wants so you can get paid - include special waivers
Bring Project current
Waivers of Claims & Liens unless listed
Statutory form issue important
Other things required includes
    List of subs/suppliers
    Schedules
    Photographs
    List of Problems

## Slide 17: Statutes of Limitation
Notes: SUBS:
AIA starts early, no tolling provision helps contractor, hurts owner
Special contractor limits wrapped around construction 1 year warranty
Special subs w/special limits negotiate with owner

## Slide 18: Changes in the Work
Develop A Rational Process That Will Actually Be Used
Markups For Fee and General Conditions
Notes: BONDS - forms
Written change order, yes but not end of the story
Charges where you can’t price it -
written auth with cap,
if no written auth no right to claim
Can’t rely on verbal changes
Finish change off in Change Order (______, no impact, no time later)
Notice provision applicable here
Markup of contractor & subs (do it front end)
SITE Conditions/ Unit prices