## Slide 1: Negotiating an “Implementation” Consent Decree
Rosemary G. Spalding
SPALDING & HILMES, PC
Presentation to
NACWA & Wet Weather Partnership Workshop
Chicago, IL
June 1, 2006

## Slide 2: Agenda
Introduction
Background
Underlying Principles of Implementation CD
Key Negotiation Issues
Lessons Learned
Conclusion

## Slide 3: Introduction
Share City of Indianapolis’ Experiences:
  attempting to obtain approval of CSO Long-Term Control Plan
  negotiating an “implementation” consent decree
Notes: <number>
<footer>
<header>
<date/time>

## Slide 4: Introduction
  Other Recent “Implementation” Consent Decrees
  D.C. Water and Sewer Authority
  WSSC/Baltimore County, Maryland
  Louisville
  Northern Kentucky Sanitary District No. 1
Notes: <number>
<footer>
<header>
<date/time>

## Slide 5: Background
Indianapolis’ Water Quality Program
Two Advanced Wastewater Treatment Plants
Collection System
  Separate Sanitary Sewer System
    encompasses ≈ 222 square miles
    includes ≈ 185 miles of interceptor sewers
    at one time included 16 constructed SSO relief points -- all but 3 eliminated and those are scheduled to be eliminated in 2007
Notes: <number>
<footer>
<header>
<date/time>

## Slide 6: Background
Collection System
  Combined Sewer System
    encompasses ≈ 56 square miles
    includes ≈ 66 miles of interceptor sewers
    includes 133 outfalls discharging into the White River and 4 of its tributaries
Notes: <number>
<footer>
<header>
<date/time>

## Slide 7: Background
Compliance with CSO Policy
  Early 1990s
    Began conducting studies and CSS modeling
  Mid-1990s:
    submitted NMC program to IDEM in 1995 (approved by IDEM in 1997) and began implementing NMCs, including several pilot projects
    developed both hydraulic and water quality models that were cited by EPA in its guidance document on modeling
    developed SRCER
Notes: <number>
<footer>
<header>
<date/time>

## Slide 8: Background
Compliance with CSO Policy
  Summer 2000
    published “Improving Our Streams in the City of Indianapolis: A Report on Options for Controlling Combined Sewer Overflows”
    hosted public education and input meetings and formed an advisory committee to ensure public participation in the development of a LTCP
  April, 2001
    submitted proposed LTCP to IDEM and EPA for approval
Notes: <number>
<footer>
<header>
<date/time>

## Slide 9: Background
Nationally leading NMC Program
Especially public outreach and information
  E-mail CSO/SSO notification
Tens of millions in “early action projects”
  Project fact sheets for most
Agency invitation to negotiate a federal consent decree to address “CSO issues”

## Slide 10: Background
City did not feel a federal decree was necessary
City was ahead of all permit requirements
EPA wanted decree because schedule would be greater than five year term of City’s permits
Compromise: implementation decree

## Slide 11: Underlying Principles of an Implementation Consent Decree
Non-adversarial
Non-punitive
Narrowly focused in scope to achieve EPA stated goal of providing enforceable mechanism for approved LTCP implementation
Consistent with permitting framework

## Slide 12: Underlying Principles
Keep LTCP approval separate from CD negotiation
CD should simply require implementation of the approved and attached LTCP.

## Slide 13
LTCP Negotiation In Ernest

## Slide 14: Key Negotiation Issues
Water Quality Standards Revision Process
  City’s goals:
    Ensure compliance with water quality standards after implementation of the LTCP and CD
    Follow Indiana’s Statutory Approach

## Slide 15: Key Negotiation Issues
Level of Control
  The key issue
  What does it mean?
  How do you determine the appropriate level of control?
  How do you describe it?
  How do you determine whether you have achieved it?

## Slide 16: Key Negotiation Issues
Schedule
  Wrong way: How fast can you spend the program cost on paper?
  This is the sole basis for EPA’s scheduling guidance

## Slide 17: Schedule Considerations – The Right Way
How many projects
Sequencing
Where located within City
Need to coordinate with other major community development programs
  Roads/transportation
  Downtown redevelopment
  Economic Development
  Historical/cultural initiatives

## Slide 18: The Right Schedule
Availability of materials, suppliers, trucks, contractors & trained labor
Availability of quality consultants & engineers to manage & inspect projects
Potential inflationary impacts on project costs due to low supply & high demand
Operational ability to bring capital “on-line”
Need to communicate & listen to the public before and during construction

## Slide 19: The Right Schedule
Allow for:
  Public opposition to specific projects
  Site constraints
  Floodway permitting (corps and others)
  Construction impacts to neighborhoods and businesses
  Equipment delivery
  Materials (concrete & steel) availability

## Slide 20: Key Negotiation Issues
LTCP Modification Process
  City: broad modification process
  Navigation is not a one time exercise
Who decides what the LTCP says about the opportunity to reevaluate?
May depend directly on whether your community faces a consent decree or not….

## Slide 21: Key Negotiation Issues
Consent decree = contract
EPA:
  No modification without EPA agreement
    In other words, dispute over whether a modification is warranted is NOT allowed to be heard by the judge
  Only relief through Federal Rule 60(b)
    Essentially, the problem has to be so unexpected or extreme that you seek and are granted relief from the contract you signed
    Extraordinarily rare, especially for issues that were expressly contemplated/negotiated by the parties (such as schedule, level of control, etc).

## Slide 22: Key Negotiation Issues
CSO community:
  Disagreement over modification subject to Dispute Resolution
    Note Burden of proof
  Failing that separate procedures for unexpected occurrences regarding key issues (level of control; schedule, etc)

## Slide 23: Key Negotiation Issues
LTCP Approval
  Should you expect it?
  From whom?
  When should you get it?
  Why is it important?

## Slide 24: Lessons Learned (so far)
A good track record should be relentlessly asserted but often is not given appropriate weight.
You must educate EPA (including EPA’s technical experts) about key aspects of your system, your circumstances and your programs.
You should define parameters and reach agreement on key components of a consent decree before beginning (or at least getting too far into) negotiations.
Negotiating approved major LTCP and decree will take substantial time and resources

## Slide 25: Lesson Learned
Negotiate who will lead on:
  LTCP approval
  Consent decree
  Note State plaintiff in Louisville and EPA citizen-intervenor
If EPA, which program (OW or OECA)
Goal: don’t let LTCP approval get tied up in decree negotiations

## Slide 26: Lessons Learned
Negotiating LTCP approvals as part of consent decree negotiations can:
  Limit your regulatory options (State and federal)
  Preclude future reevaulation of controls

## Slide 27: Conclusion
The city’s view and EPA’s view are very different regarding what an “implementation” consent decree means
Appropriate decision-making regarding LTCP approvals should come from States and EPA-OW/States and not as negotiated consent decree requirements